## Risk Matrix
Severity of Harm
|  | Negligible (A) | Minor (B) | Serious (C) | Critical (D) | Catastrophic (E)
|  | Minor Injury or property damage | Limited injury or property damage | Medically reversivle injury or significant property damage | Permanent injury or serious property damage | Life-threatening injury or catastrophic property damage
Probability of occurnence | Frequent - 5 (happens with almost every use of the device) | Control | Unacceptable | Unacceptable | Unacceptable | Unacceptable
| Probable - 4 (Occurs the majortiy of times but not with every use) | Control | Control | Unacceptable | Unacceptable | Unacceptable
| Occasional - 3 (Occurs with increased frequency) | Acceptable | Control | Control | Unacceptable | Unacceptable
| Remote - 2 (More than one occurrence per year but still unlikely | Acceptable | Acceptable | Control | Unacceptable | Unacceptable
| Improbable - 1 (Less than one occurrence per year; isolated events) | Acceptable | Acceptable | Acceptable | Control | Control
Source: https://www.orielstat.com/blog/medical-device-risk-management-plan/
Source: https://www.greenlight.guru/blog/iso-14971-risk-management

## Risk Worksheet
Risk Assessment Worksheet
(To be used in conjunction with Risk Matrix)
Date: | June 15th 2020
Risk Assessment Objective: | Evaluate risk associated with gVent failure and appropriate control systems response
Period of Examination: | New Addition
Participants: | SMCI: Jeff, Clement, Daryl, Reza ECA: Joseph, Andrew, Rob Doucette, Rob Robinson
Identify Risk Scenario (Cause) | Affected component/section | Impact / Consequence | Probability Rating (No Safeguards) | Severity of Harm | Risk Level (No Safeguards) | Recommended/Current Mitigations and Controls | Probability Rating with Safeguards | Risk Level with Safeguards | Risk Treatment Strategy And Mitigation Plan | Residual Risk
1. No/Low Flow
Loss of pressure from main supply | Overall |  | 1 | E | 1E - Control | Redundancy needed, built-in auxillary oxygen supply? Currenly have check valve to allow breath when inspiratory valve is closed. | 2 | B | (Sample code and/or recommendations here) | (for example) 2B further risk reduction limited by matrix (If there is nothing else that can be done this is the vernacular for it)
Faulty fs6122 sensor | Overall | Inaccurate/No flow feedback | 1 | E
Potentiometer not responsive | Potentiometer/overall | No flow/pressure control | 1 | E | 1E - Control | Redundancy needed, built-in physical switches with certain presets? |  |  | Build presets into Arduino that can be activated and override existing control with physical switches
2. Excess Flow
Faulty
3. Reverse/Misdirected Flow
Patient coughing
4. High Level
Excess water fill in the reservoir
5. Low Level
Insufficient water fill in reservoir
6. High Pressure
Possible pressurization in water chamber?
7. Low Pressure
8. High Temperature
Excess heat exposure to ventilator
9. Low Temperature
Conducted operations in location where
10. Reactive Hazards
N/A
11. Composition / Phase Change
12. Contamination
13. Instrumentation
14. Corrosion / Erosion
- corrosive service |  | -insufficient corrosion monitoring (corrosion coupons)
15. Service Failure
LCD display not working
Loss of main power
Loss of instrument air (do we have any to ensure valves and everything fail in the appropriate way?)
16. Mode of Operation
17. Abnormal Operations
18. Start-up / Shutdown
19. Human Factors
20. Previous Incidents
21. Decontamination / Maintenance
22. Other
What could go wrong? What could stop us from achieving our business objectives? | If the risk review is pertaining to a set of drawings, list the drawing number that the risk scenario applies to. | What is the result or consequence of the risk scenario? | Minor, Moderate, Serious or Critical - Consider each Risk Category separately. | What is the probability of the impact occurring with no safeguards in place: Remote, Unlikely, Likely or Frequent? | What is the risk level with no safeguards in place: Low, Medium, High or Extreme? | What safeguards or measures are in place to prevent the impact from occurring? | What is the probability of the impact occurring with safeguards in place: Remote, Unlikely, Likely or Frequent? | What is the risk level with the safeguards in place: Low, Medium, High or Extreme? | If the risk is deemed to be unacceptable with the existing safeguards in place, what can be done about it? | What is the risk level with additional safeguards in place: Low, Medium, High or Extreme?

## Action items
Risk Review Action Items
Subject | gVent HAZOP
Date | June 15th 2020
By | gVent team
Rev | A
Item | Original Issue / Recommendations | Resolution | Completed Y/N | To be completed by and date | Comment
1 | Need to figure out default failed state for all valves, pumps, electronic equipment etc. In the case the pressure sensors fail (one or both) |  |  |  | I think this is the most important thing to find out and determine if all physical components fail, what can the Arduino do to make sure everything is safe and what state does that look like (cutoff of supply, revert to default regulated flow rate etc.)
2 | Find out about failure rates of sensors?? Call manufactureres to find out??
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22

## Deviations
Risk Assesment Deviations
Current Safety Features:
Item | Deviation | Example | Inherent pressure limited design
1 | Low / No Flow | control valve fails close, manual valve closed | Inspiratory check valve
2 | High Flow | control valve fails open, manual valve opened | High/low RR alarm
3 | Reverse / Misdirected Flow | check valve failure, manual valve open / close | High/low VTIDAL alarm
4 | Leak / Rupture | leak | High/low Pinsp and PEEP alarm
5 | Loss of Containment | spill, overflow | High/low MV alarm
6 | Hydraulic Surge |  | Apnea Alarm
7 | High Pressure |  | Pressure mismatch alarm
8 | Low Pressure |  | Flow mismatch alarm
9 | Vacuum | steam out of equipment, cooling of isolated equipment
10 | HP/LP Interface | spec break, dump valve, choke valve, PSV outlet
11 | High Temperature? (Temperature depends on deployment area)
12 | Low Temperature?
13 | Freezing? | control valve JT, hydrate, external temperature
14 | Brittle Fracture?
15 | High Level (or lnterface Level)
16 | Low Level (or lnterface Level)
17 | Contamination | water contamination,
18 | Internal Impact | well debris, valve/instrument internals
19 | Corrosion / Erosion (Longer term use)
20 | External Impact
21 | Poor Visibility / Accesibility
22 | Indoors / Outdoors (More related to temperature)
23 | Effects Towards Other Equipment
24 | Effects From Other Equipment
25 | Maintenance Risks??
26 | Start-up / Shutdown Hazards
27 | Operator Error